Project Title: Integrated child protection interventions for the most affected children and caregivers in the Gaza Strip

#### Overall Project Status

The project is progressing exceptionally well across all output areas, with most indicators showing substantial advancement toward annual targets. The high improvement rates in trauma coping skills (84%) and psychological wellbeing (94%) demonstrate the effectiveness of our interventions. The strong integration of SEL and Mind-Body techniques by trained education staff (97%) indicates successful capacity building.

While challenges remain in reaching all targeted beneficiaries, the current trajectory suggests we are on track to achieve or exceed most annual targets by the end of the project period.

#### Project outputs:

- Targeted IDPs in shelters and surrounding communities receive comprehensive trauma-healing services

The project has demonstrated exceptional progress in delivering trauma-healing services to IDPs in shelters and surrounding communities. We have successfully conducted 1,026 Mind-Body Medicine Self-Care Workshops, reaching a total of 22,288 participants (6,819 boys, 9,115 girls, 2,200 men, and 4,154 women). This represents a significant advancement toward our overall target of 60,000 participants.

Workshop participants have shown remarkable improvement in trauma coping skills, with an average improvement rate of 84%, substantially exceeding our target of 60%. These workshops have equipped participants with essential stress and trauma management techniques, including Soft-Belly Relaxation, Shaking and Dancing, and Safe Place Imagery.

The Mind-Body Skills Groups (MBSGs) have been particularly impactful, with 99 groups completed, engaging 940 participants (186 boys, 419 girls, 33 men, and 302 women). These groups have achieved an impressive 94% improvement rate in psychological wellbeing among participants, significantly surpassing our 80% target. The gender distribution shows strong engagement from females (721) compared to males (219), reflecting our commitment to inclusive programing.

Key Indicators:

- Number of IDPs participating in MBM Self-Care Workshops: 22,288 (Target: 60,000)

  - Gender breakdown: 13,269 females (59.5%), 9,019 males (40.5%)

  - Age breakdown: 15,934 children (71.5%), 6,354 adults (28.5%)

- Percentage of IDPs showing improved trauma coping skills: 84% (Target: 60%)

- Number of Mind-Body Skills Groups conducted: 99 (Target: 5)

- Number of traumatized IDPs participating in MBSGs: 940 (Target: 2,750)

  - Gender breakdown: 721 females (76.7%), 219 males (23.3%)

  - Age breakdown: 605 children (64.4%), 335 adults (35.6%)

- Percentage of MBSG participants showing improved psychological wellbeing: 94% (Target: 80%)

- Education staff and teachers develop skills to support trauma-affected children

The project has made substantial progress in equipping education staff with skills to support trauma-affected children and integrate MHPSS techniques into teaching practices. We have successfully conducted 5 training groups for education staff, reaching a total of 194 participants (72 males and 122 females).

The trained education staff have demonstrated exceptional improvement in integrating Social and Emotional Learning (SEL) and Mind-Body Medicine techniques into their teaching practices, with an average improvement rate of 97%, significantly exceeding our target of 80%. This high improvement rate indicates the effectiveness of our training methodology and the commitment of education staff to implement these approaches.

To reinforce training concepts and extend the project's impact, we have sent 2,100 SMS messages to students and teachers, providing information on mind-body techniques and self-care skills. This represents a substantial increase from the previously reported 1,093 messages.

Additionally, 88 weekly clinical sessions have been conducted to provide ongoing support and mentorship to education staff implementing these techniques in their classrooms.

Key Indicators:

- Number of education staff receiving Mind-Body Medicine Training: 194 (Target: 1,150)

  - Gender breakdown: 122 females (62.9%), 72 males (37.1%)

- Percentage of trained staff showing improved integration of MBM and SEL skills: 97% (Target: 80%)

- Number of education staff and students receiving SMS messages: 2,100 (Target: 6,150)

- Number of weekly clinical mentorship sessions provided: 88 (Target: 3,360)

- Community awareness and participation

The project has significantly expanded community awareness of MHPSS resources and ensured community participation in project development. We have successfully reached 4,173 affected and at-risk individuals who have been informed or consulted about project implementation, representing substantial progress toward our target of 9,000.

Our commitment to protection and safeguarding is evident in the number of beneficiaries with access to report Sexual Exploitation and Abuse (SEA), which has reached 20,624 individuals. These beneficiaries have received awareness sessions and materials during project implementation, representing significant progress toward our target of 54,000.

Key Indicators:

- Number of affected and at-risk population informed/consulted: 4,173 (Target: 9,000)

- Number of beneficiaries with access to report SEA: 20,624 (Target: 54,000)